## User Stories Cs482(Team Fabrizi
ID | Story Title | Points | Priority | As a/an [user] | I want [functionality] | So that [value] | User Story | NFR | Definition of Done / Blockers | Epic ID | Status | Notes
E0 | Example |  | Medium | Professor | to create requirements | my students understand. | As a/an Professor, I want to create requirements, so that my students understand. | NFR2 | When NFR2 is complete | -- | Open | A responsible adult must accept on behalf of the child
M0 | Manager invites Coach | 1 | High | Manager | to be able to invite a coach | the team has a coach | As a/an Manager, I want to be able to invite a coach, so that the team has a coach | NFR0 | When NFR0 is complete | -- | Open | Admin,Adult,Child,Coach,Teammanager,Guest
M1 | Manager Invites Players | 1 | High | Manager | to be able to invite players to join my roster | players can join the team | As a/an Manager , I want to be able to invite players to join my roster, so that players can join the team | NFR1 | When NFR1 is complete | -- | Open
U0 | View score | 2 | High | User | to see the live socre of the game | I can watch the game from the website | As a/an User, I want to see the live socre of the game, so that I can watch the game from the website | NFR2 | When NFR2 is complete | -- | Open | Admin
G0 | Guest Perm. | Permission is not a user story. This is a NFR. |  | Guest User | to access the website | I can see the Live scores, schedules, and chat | As a guest user I want to be able to view the live scores of games along with scheduels | NFR3 | When NFR3 is complete | -- | Open | Adult(Parent,Coach,Teammanager)
P0 | Adult accepting invite for child | 1 | High | Parent | to accept a team invite for my child | a minor can join a team | As a/an Parent, I want to accept a team invite for my child, so that a minor can join a team | NFR4 | When NFR4 is complete | -- | Open | User(Adult,Guest,child)
U1 | Rating system for team manager | 2 | Low | User | to be able to rate my team manager | I can my managers performance | As a/an User, I want to be able to rate my team manager, so that I can my managers performance | NFR5 | When NFR5 is complete | -- | Open
U2 | Score Board | 1 | High | User | to be able to view Live scores | keep track of ongoing games | As a/an User, I want to be able to view Live scores, so that keep track of ongoing games | NFR6 | When NFR6 is complete | -- | Open
U3 | Seaon Standings | 1 | High | User | to be able to view current standings | keep track of overal season standings | As a/an User, I want to be able to view current standings , so that keep track of overal season standings | NFR7 | When NFR7 is complete | -- | Open
A0 | Register | 3 | High | Adult | to be able to register myself | I can register myself | As a/an Adult, I want to be able to register myself, so that I can register myself | NFR8 | When NFR8 is complete | -- | Open
U2 | Chat Room | 5 | High | User | to be able to communitcate | theres a message board that can be used to follow along with other users | As a/an User, I want to be able to communitcate, so that theres a message board that can be used to follow along with other users | NFR9 | When NFR9 is complete | -- | Open
A2 | Parental Concent | * | High | Adult | to be able to supervise my childs actions | I can decide whether my child joins a team or not | As a/an Adult, I want to be able to supervise my childs actions, so that I can decide whether my child joins a team or not | NFR10 | When NFR10 is complete | -- | Open
U3 | Login / Logout | 1 | High | User | to be able to login to an account | i can access my saved information | As a/an User, I want to be able to login to an account, so that i can access my saved information | NFR11 | When NFR11 is complete | -- | Open
A3 | Upload Picture/Video | 5 | Medium | User | to post a picture or video of a game | other users can view it | As a/an User, I want to post a picture or video of a game, so that other users can view it | NFR12 | When NFR12 is complete | -- | Open
M2 | Request a replacement | 2 | Low | Manager | to request a replacement | the team has a manager | As a/an Manager, I want to request a replacement, so that the team has a manager | NFR13 | When NFR13 is complete | -- | Open
ADM0 | Chat Restrictions | * | Medium | Admin | to be able to moderate who has access to chat previllages | the chat remains family friendly | As a/an Admin, I want to be able to moderate who has access to chat previllages, so that the chat remains family friendly | NFR14 | When NFR14 is complete | -- | Open
M3 | Update score and stats | 3 | High | Manager | to be able to update the score and stats of game | users can view the score and stats of the game | As a/an Manager , I want to be able to update the score and stats of game, so that users can view the score and stats of the game | NFR15 | When NFR15 is complete | -- | Open
M4 | Store Team Info. | 2 | HIgh | Manager | to be able to store team info. | I have access to my roster | As a/an Manager , I want to be able to store team info., so that I have access to my roster | NFR16 | When NFR16 is complete | -- | Open
ADM1 | Access Database | This is not a story (too vague). The Admin should not have unrestricted access to your app database. You should provide that for the admin on the appropriate stories the admin requires a full crud. | High | Admin | to be able to access teams database | I have the ability to update and delete information | As a/an Admin, I want to be able to access teams database, so that I have the ability to update and delete information | NFR17 | When NFR17 is complete | -- | Open
U5 | View Calendar | 3 | Medium | User | to be able to view my schedule | I can know when games are being played | As a/an User, I want to be able to view my schedule, so that I can know when games are being played | NFR18 | When NFR18 is complete | -- | Open
ADM1 | Season Locking | 1 | High | Admin | to be able to restrict team changes | once the season starts all teams are final | As a/an Admin, I want to be able to restrict team changes, so that once the season starts all teams are final | NFR19 | When NFR19 is complete | -- | Open
ADM2 | Pictures with minor | I believe you misunderstood this requirement. The admin should not the only one to flag content. Any user can flag their post if it contains a minor on it. And Guest should *NOT* be able to view them. | medium | Admin | to be able to mark pictures as having minors | guests can view them | As a/an Admin, I want to be able to mark pictures as having minors, so that guests can view them | NFR20 | When NFR20 is complete | -- | Open
ADM3 | Manager Replacement | * | Medium | Admin | to replace Managers | if a manager quits they can be replaced | As a/an Admin, I want to replace Managers , so that if a manager quits they can be replaced | NFR21 | When NFR21 is complete | -- | Open
U6 | Color Scheme | Not a user story, this is a NFR. When something affects the ENTIRE system it is an NFR. | Low | User | to have the color scheme be Orange, Black, and White | the website is fitting for the area inwhich the league is taking place | As a/an User, I want to have the color scheme be Orange, Black, and White, so that the website is fitting for the area inwhich the league is taking place | NFR22 | When NFR22 is complete | -- | Open
U7 | Game History | 1 | Medium | User | to be able to view past scores | games have progressed | As a/an User, I want to be able to view past scores, so that games have progressed | NFR23 | When NFR23 is complete | -- | Open | Time Machine
U8 | Game type | * | Medium | User | to see the game type | I know if it is a normal,playoff, or final | As a/an User, I want to see the game type, so that I know if it is a normal,playoff, or final | NFR24 | When NFR24 is complete | -- | Open
U9 | Schedule | * | High | User | to see my schedule | I know when I need to play | As a/an User, I want to see my schedule, so that I know when I need to play | NFR25 | When NFR25 is complete | -- | Open
A4 | Disclaimer | * | High | Adult | to see what I am subjecting my child to in terms of the league | Im aware of the dnagers and commitment of the league | As a/an Adult, I want to see what I am subjecting my child to in terms of the league, so that Im aware of the dnagers and commitment of the league | NFR26 | When NFR26 is complete | -- | Open
ADM4 | Prevent A child from being on multiple teams | You cannot create a story to prevent something, or not do something and say that requires 3 points of effort. This should be included on the definition of done of the create team or team invite story | Medium | Admin | to prevent a player from being on multiple teams | elligibillity rules are followed | As a/an Admin, I want to prevent a player from being on multiple teams, so that elligibillity rules are followed | NFR27 | When NFR27 is complete | -- | Open
Missing requirement: Live Matches. U2 comes close but is not quite what the live match requirement is.
Missing requirement: Playoff generation. No story mentions the playoff gen.
Note on I2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: In the template spreadsheet, there was a tab for NFRs. Without this tab I have no idea what you mean by NFR2, NFR3, etc. I cannot say if what you created are indeed NFRs or not. It seems excessive to have 27 NFR. I think you did not understand what is a NFR, and just added sequential numbers for each story.
Note on B3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: You should have removed the example.
Note on C4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: The coach is already in the system. Therefore inviting is a very simple flag.
Note on C5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Both the players and the coach data needs already to be on the system. Inviting becomes a simple flag/field to set up.
Note on C8: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Accepting an invite is simple "Yes/No" option and updating one flag. That is barely 1 point.
Note on C9: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Rating system is just create one field with predefined options
Note on C10: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: To keep updating the live match it does require a lot of work. Just to view it, is a simple read operation.
Note on C11: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: If the admin updates the scores after each match, then all info on the season standings should already be saved. Just displaying such standings is barely 1 point.
Note on C14: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Parental disclaimer can even be done statically without any code (and as such worth 0 points). If there is some code (and I mean real back-end nodejs and database code) then it would be max 1 point, as you are just updating one boolean on a kid profile.
Note on B15: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: I added logout as well
Note on C15: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Login/logout is very simple code. It is worth 1 point because there is nothing less for it.
Note on C18: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This will depend a lot on how you are planning to implement this. If this is actual moderation done by an admin, it could be worth some points but then the chat would have to be unavailable unless there is an admin on it. I dont think this is feasible, and you probably misunderstood a requirement.
Note on C19: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This is just updating textual data.
Note on B20: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: I would say "Create Team" would be a better title (and description) for this story than "store team info"
Note on C23: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Season locking is just updating a flag (on/off). 3 points is too much, 1 is already too much.
Note on G24: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Guest should NOT view them
Note on C25: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This is too similar to M2. You need to create a more generic story that involves Admin and Manager, and be more specific on the definition of done.
Note on E26: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Incorrect the User does not want these colors. The person you interviewed wanted these colors for the ENTIRE website.
Note on C27: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: The scores are already saved on the app. Display a previous one is just a simple read operation.
Note on C28: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This story is redudant with Schedule or View Calendar. If you look at your schedule or calendar, you want to see the game type, location, and any other detail on it. No need to create another story for a simple detail.
Note on C29: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: How is this different from View Calendar? Even the story description are almost the same.
Note on C30: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: How is this different form A2 Parental Consent?